ReSaMMé

Partnership Meeting

10th of November 2006

Alexander Beach Hotel & Convention Center

Alexandroupoli, Greece

Minutes

The ReSaMMè meeting started at 6.30 and ended at 8.30 p.m. and had the following agenda:

  - ReSaMMè project partnership management and coordination

  - analysis of project activities

  - state of the art of project activities

Participants:

ARPA Ingegneria-Ambientale – Emilia-Romagna

Mentino Preti

Maurizio Morelli

Nunzio De Nigris

ERVET – Emilia-Romagna Regional Development Agency

Lucia Calliari

University of Perpignan -  BDSI

Isabelle Lortal

ICM – Institut De Ciències del Mar

Belén Alonso

University of  Genoa - DIPTERIS

Nicola Corradi

Ileana Balduzzi

University “La Sapienza” of Rome - DST

Eleonora Martorelli

Francesco Falese

Democritus University of Thrace

Vassilios Tsihrintzis

Mr. Preti thanks all the partners for taking part to the meeting and underlines the importance and necessity at the present stage of the project both to develop the mutual knowledge among all the ReSaMMè partners and to plan and create an efficient partnership coordination.

In fact the present meeting represents the first real chance to make acquaintance among all the ReSaMMè partners after the project starting in order to exchange detailed information about each partner with regard both to its general asset and specifically to its contribution to the project.

Then he introduces Mr. De Nigris and Mr. Morelli, explaining their role in the project and Mrs. Calliari from ERVET S.p.a.

Mrs. Calliari briefly presents the role of ERVET S.p.a, the Emilia-Romagna Regional Development Agency, that provides for technical assistance to ARPA in the management of ReSaMMè project, with specific attention to the partnership coordination. Therefore she asks the partners to keep constantly in touch in order to optimize the communication with respects to management aspects, such as the next progress report t be presented in December 2006.

Mr. Preti suggests to analyse together in detail the ReSaMMè application form, so to pass through all the steps of each phases described in the document. This will allow to check the point of view of each partner regarding every single activities and to update the information on the state of art of each step of the project.

Then a brief discussion and mutual exchange among the partners followed.

Mr. Preti then reminds the main goal of the B Phase, which is the detailed definition and planning of the research, and the time left (around two months) for the conclusion of this phase. Therefore, in consideration of the current activities of sea-campaign/research definition, all the partners present and exchange their background, experience and specificities focusing on technical aspects related to research cycle (data recognition and analysis, geophysical an geognostical research etc.)

Vassilios Tsihrintzis explains that they will base their research on a set of data (two drilling) acquired from a local oil company and he introduces the problem related to the realization of an eventual sea-campaign, which will be too expensive for their budget.

Mrs. Martinelli underlines the importance of the methodology itself in the realization of a successful research and also the importance of defining technical standards shared by all the partners, in order to optimize the use of the data acquired during previous researches.

Mr. Preti thanks all the partners for their contribution to the discussion and closes the meeting.